## Sheet1
Issue No. | Interface Name | Issue Details | Issue Date | Status | Issue Type | Estimated Time
1 | Attendnace Management | Attendance device problem for some employees |  | Solved | Development | Solved
2 | Attendnace Management | Exception report for Inpunch & Outpunch |  | Solved | Report | Solved
3 | Final Settlement | Final settlement report |  | Pending | Report And Development | After getting the feedback on Fianl settelment (interface) CslSoft will send the report
4 | Last working Date | Last working date for Resigned Employees is not showing in bulk seperation | from the beginning | Solved |  | 15/01/2014
5 | Attendnace Management | In attendance process screen old month datas are not showing properly. |  | Pending |  | Will discuss on 19th Jan
6 | PMS - Basic Informatio | need a column for entering the bus route number and pickup point |  | Solved |  | Solved
7 | Leave Management | OL balance updation for Non ESI Candidates | from the beginning | Solved |  | 2014-09-01
8 | Leave Management | OL balance cancellation for ESI Candidates in payslip | from the beginning | Pending |  | Need to discuss with Mgt of CslSoft
9 | Loan & Advance Management | If the Loan or advance is less than the earning it should not be deducted. | from the beginning | Pending |  | Need to discuss with Mgt of CslSoft
10 | Reports | OT summary report = (actual OT - Paid OT) | from the beginning | Solved |  | 2014-09-01
11 | Reports | In Appointment Order Employement date is showing the current date but it should be Date of Joining | from the beginning | Solved |  | 2014-09-01
12 | Reports | In Job application the Esi Number is showing wrongly and in DOJ it is showing The time Too it should be deleted. | from the beginning | Solved |  | 2014-09-01
13 | Reports | In Day wise work status the previous months attendance is not showing properly for Ex: 08.05.2013 | from the beginning | Pending |  | Will discuss on 19th Jan
14 | Reports | In Daily absenteeism report, we need date when we convert to excel |  | Solved |  | 2014-12-01
15 | Reports | There is a difference in Earned wages between ESI Statement and Payslip |  | Solved | For Checking iam giving an emp no.000069 Amsa. Kindly compare her Total earnings in ESI Statement and her payslip | 2014-12-01
16 | Reports | We need Unit filter in List of employees report |  | Solved |  | 13/01/2014
17 | Reports | In Payslip Multi month, the report is not generating properly |  | Solved |  | 14/01/2014
18 | Reports | Also need Department in New recruitment list. Now it is showing only designation |  | Solved |  | 2014-12-01
19 | Reports | We need a report stating the list of employees for whom salary / dept change revision has been made |  | Solved |  | 2014-12-01
20 | Query Manager | In Employee Salary Info, we need Employee type such as worker / Staff |  | Solved |  | Solved
21 | Reports | We need a report consiting of shift assigned for a employee for that particular week. |  | Solved |  | 13/1/2014